## page1
TaskID | Task | Epic | Assignee | Status | Milestone | Estimated Hours | Remaining Hours | log
OMS-1 | Develop CMP Template and Define Sections | CMP | Menna | Completes | Release 1 | 2 |  | 1
OMS-2 | Fill Content in CMP & Complete CMP Documentation | CMP | Hager | Completes | Release 1 | 2 |  | 2
OMS-3 | CMP Review | CMP | Mario | Completes | Release 1 | 1 |  | 1
OMS-4 | Develop PMP Template | PMP | Mario | Completes | Release 1 | 1 |  | 0.5
OMS-5 | Complete PMP Documentation | PMP | Mohamed | Completes | Release 1 | 3 |  | 2
OMS-6 | PMP Review | PMP | Hassan | Completes | Release 1 | 1 |  | 1
OMS-7 | Prepare SIQ Draft | SIQ | Mena | Completes | Release 1 | 2 |  | 1
OMS-8 | Finalize SIQ Document | SIQ | Hassan | Completes | Release 1 | 4 |  | 5
OMS-9 | SIQ Review | SIQ | Menna | Completes | Release 1 | 1 |  | 1
OMS-10 | Create Risk Sheet | risk | Mohamed | Completes | Release 1 | 5 |  | 4
OMS-11 | Create CRS Template | CRS | Hassan | Completes | Release 1 | 1 |  | 0.5
OMS-12 | Complete CRS Documentation | CRS | Hassan | Completes | Release 1 | 3 |  | 2
OMS-13 | CRS Review | CRS | Mario | Completes | Release 1 | 1 |  | 1
OMS-14 | Complete SRS Documentation | SRS | Mena | Completes | Release 1 | 5 |  | 6
OMS-15 | SRS Review | SRS | Mario | Completes | Release 1 | 2 |  | 2