## Release#1
Day | Planned | Consumed | Team Availability |  |  |  | Deliverable | % Completed | Comments | Points
1 | 15 | 15 | 66 |  |  |  | Update SRS | 100% | Menna | 5
2 | 20 | 20 |  |  |  |  | update TCs | 100% | Menna | 7
3 | 25 | 20 |  |  |  |  | complete frontend connection with backend | 100% | Mina | 6
4 | 30 | 30 |  |  |  |  | 1st TCs Run | 100% | Mario | 6
5 | 40 | 42 |  |  |  |  | 1st TCs Run | 100% | Mohamed | 5
6 | 50 | 56 |  |  |  |  | Test Excution Report | 100% | Mohamed | 4
7 | 60 | 66 |  |  |  |  | Bug Report | 100% | Mina | 3
[7 empty] | code Refactor based | 100% | Hager | 4
[7 empty] | code Refactor based | 100% | Hager | 3
[7 empty] | 2nd TCs Run | 100% | Mario | 7
[7 empty] | RTM | 100% | Mohamed | 5
Risks | [6 empty] | Review SRS& TCs | 100% | Hager | 5
Actions
[11 empty] | Members | Sum of Points | Sum of Done
[11 empty] | Mohamed | 14 | 14
[11 empty] | Mario | 13 | 15
[11 empty] | Mena | 9 | 9
[11 empty] | Hager | 12 | 14
[11 empty] | Menna | 12 | 14
Issues | [10 empty] | Total | 60 | 66
ID | Initiator | Probability | Impact | Description | Handling | Actions
Issue_ID_1 | Hassan | high | high | A team member is required to perform mandatory military service | Mitigate | reassign the member's tasks to others. adjust the project timeline