## Sheet1
Risk_ID | Risk description | Impact description | Impact Level (1-5) | Probability Level (1-5) | Priority Level (Impact * probability) | Mitigation Notes | Status | Notes | Date Identified
Risk_1 | Lack of Experience | some of the team members not have sufficient experience in website development | 4 | 5 | 20 | involve team members into training sessions | Open |  | 30-3-2026
Risk_2 | Low productivity | Reduced productivity due to scholarship courses and ISTQB certifications exams | 2 | 4 | 8 | setting plan to split tasks and prioritize it and balance between work and study | Open |  | 30-3-2026
Risk_3 | development mistakes | Team members may write incorrect code during development due to lack of experience | 5 | 4 | 20 | asign members who have high technical skills to review code and test each module right after it is written. | Open |  | 30-3-2026
Risk_4 | integration problems | Code written separately may not integrate well due to different approaches. | 3 | 4 | 12 | Hold regular check and meeting so everyone stays aligned on implementation style. | Open |  | 30-3-2026
Risk_5 | Military Service Absence | A team member is required to perform mandatory military service | 5 | 5 | 20 | reassign the member's tasks to others. adjust the project timeline and inform the customer of the change in resources. | Open |  | 30-3-2026
Risk_6 | Limited Tool Knowledge | The team may not know how to use tools that could speed up development. | 4 | 2 | 8 | provide training sessions | Open |  | 30-3-2026