## Release#1
Day | Planned | Consumed | Team Availability |  |  |  | Deliverable | % Completed | Comments | Points
1 | 25 | 15 | 66 |  |  |  | Create Frontend JS {auth} | 100% | Mina | 15
2 | 30 | 20 |  |  |  |  | Create Frontend HTML CSS | 100% | Menna | 15
3 | 35 | 23 |  |  |  |  | Create Backend | 100% | Mario | 20
4 | 40 | 26 |  |  |  |  | Create Backend arch | 100% | Hager | 20
5 | 50 | 42 |  |  |  |  | Code Review | 60% | Mohamed | 10
6 | 60 | 70 |  |  |  |  | Create Release Plan | 100% | Mohamed | 1
7 | 70 | 80
Risks
Actions
[11 empty] | Members | Sum of Points | Sum of Done
[11 empty] | Mohamed | 11 | 8
[11 empty] | Mario | 20 | 20
[11 empty] | Mena | 15 | 12
[11 empty] | Hager | 20 | 20
[11 empty] | Menna | 15 | 20
Issues | [10 empty] | Total | 81 | 80
ID | Initiator | Probability | Impact | Description | Handling | Actions
Issue_ID_1 | Hassan | high | high | A team member is required to perform mandatory military service | Mitigate | reassign the member's tasks to others. adjust the project timeline