## Release#1
Day | Planned | Consumed | Team Availability |  |  |  | Deliverable | % Completed | Comments
1 | 36 | 18 | 55 |  |  |  | Update SRS | 100% | Mina
2 | 37 | 18 |  |  |  |  | Review SRS | 100% | Hassan
3 | 38 | 27 |  |  |  |  | Review SRS | 100% | Menna
4 | 39 | 27 |  |  |  |  | Update PMP | 100% | Hassan
5 | 40 | 35 |  |  |  |  | Review PMP | 100% | Mohamed
6 | 41 | 37 |  |  |  |  | Update CMP | 100% | Hager
7 | 42 | 42 |  |  |  |  | Review CMP | 100% | Menna
[7 empty] | Update CRS | 100% | Hassan
[7 empty] | Create RTM | 100% | Mohamed
[7 empty] | Review RTM | 100% | Mario
[7 empty] | Create TCs drafts | 100% | Menna
Risks | [6 empty] | Review TCs drafts | 100% | Hager
ID | Topic | Probability | Impact | Description | Handling | Actions | Re-Update SRS | 100% | Mina
R_1 | productivity | medium | medium | Reduced productivity due to scholarship courses and ISTQB certifications exams | Accept
R_2 | Resource | high | medium | A team member is required to perform mandatory military service | Mitigate | reassign the member's tasks to others. adjust the project timeline
R_3 | holidays | high | high | There is a shortage within the team due to the Christian holidays | Accept
Issues
ID | Initiator | Probability | Impact | Description | Handling | Actions
Issue_ID_1 | Hassan | high | high | A team member is required to perform mandatory military service | Mitigate | reassign the member's tasks to others. adjust the project timeline