## Sheet1
Review comment | when | who | statues
progress sheet is not in official github | 4//4/2026 | hassan | open
release 2 planning sheet is not created yet | 4//4/2026 | hassan | open
google sheet is not accessed for team members | 4//4/2026 | hassan | open
Ci list is not updated with last version | 4//4/2026 | hassan | open
no visibility for project planning estimation | 4//4/2026 | hassan | open
baseline was not done in the plan time | 4//4/2026 | hassan | open
software requirements are not detailed enough | 4//4/2026 | hassan | in progress