## الورقة1
TaskID | Task | Epic | Assignee | Status | Milestone | Estimated Hours | Remaining Hours | log
OMS-1 | Develop CMP Template and Define Sections | CMP | Menna | In Progress | Release 1
OMS-2 | Fill Content in CMP & Complete CMP Documentation | CMP | Mohamed | Not Started | Release 1
OMS-3 | CMP Review | CMP | Mario | Not Started | Release 1
OMS-4 | Develop PMP Template | PMP | Mario | Completes | Release 1
OMS-5 | Complete PMP Documentation | PMP | Mohamed | Completes | Release 1
OMS-6 | PMP Review | PMP | Mena | Not Started | Release 1
OMS-7 | Prepare SIQ Draft | SIQ | Hassan | Completes | Release 1
OMS-8 | Finalize SIQ Document | SIQ | Mena | Completes | Release 1
OMS-9 | SIQ Review | SIQ | Hager | In Progress | Release 1
OMS-10 | Create Risk Sheet | risk | Mohamed | Not Started | Release 2
OMS-11